## Sheet1
Task | Description | Completed | Assign | Link | Completed_by
Data Cleaning | Income data | Yes | Milly | https://drive.google.com/file/d/0B1ETDZTkdcE3Wm85anNfWHN3c2c/view?usp=sharing | morning
Data Cleaning | Data Load | Yes | Christina, David |  | morning
Data Validation | Validate data quality | No | Christina, David |  | morning
Github Check | Check whether the github has been loaded with data | Yes | David |  | morning | https://github.com/live-act/govhack2017
Github Code Check | Check whether we can run programs from the code download from the github | WIP | David |  | morning | https://github.com/live-act/govhack2017
User Experience Testing | Test whether the outputs will pass simple sanity check | No | Christina |  | morning | https://eccdm.shinyapps.io/act_liveability_profile_index/
Data Validation | Check the income data from ABS | Yes | Andy |  | morning
User Experience Testing | Test colour and effect; whether size will be out of proportion | No | Christina |  | morning
User Experience Testing | Check the graphic of the website | No | Milly |  | morning
Web Design | Design a web page containing explanations of our work; preferrable embed our outputs | No | Milly |  | morning
Model Outputs Test | Test whether outputs will make sense | No | Andy |  | morning
Check dataset in the depository |  | No | Christina, David |  | morning
Github finalise | finalise the github repository | No | Andy |  | morning | https://github.com/live-act/govhack2017
Check postcode accuracy | somehow the visual map is based on inaccurate postcode. check required | No | David |  | morning